## Predicted
Data Analytics Project |  | Key:
Completed by: Henry |  | # task | \@ milestone |  | ## PSM activity |  |  |  | "= critical path"
Note: each interval represents a day in the week (Mon-Fri) | [10 empty] | School Holiday break
| Week starting 18/3 |  |  |  |  | Week starting 25/3 |  |  |  |  | Week starting 1/4 |  |  |  |  | Week starting 8/4 |  |  |  |  | Week starting 15/4 |  |  |  |  | Week starting 22/5 |  |  |  |  | Week starting 29/5 |  |  |  |  | Week starting 6/5 |  |  |  |  | Week starting 13/5 |  |  |  |  | Week starting 20/5 |  |  |  |  | Week starting 27/5 |  |  |  |  | Week starting 3/6 |  |  |  |  | Week starting 10/6 |  |  |  |  | Week starting 17/6 |  |  |  |  | Week starting 24/6 |  |  |  |  | Week starting 1/7 |  |  |  |  | Week starting 8/7 |  |  |  |  | Week starting 15/7 |  |  |  |  | Week starting 22/7 |  |  |  |  | Week starting 29/7 |  |  |  |  | Week starting 5/8
Tasks: | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
Preliminary:
Research question
# Brainstorm Ideas
# Finalise Research Question
# Locate Data Sources
# Analyse Data Sources
\@ Complete Research Question
\@ Submit Research Question
Gantt chart
# Identify Tasks
# Allocate Durations
# Identify Milestones
# Identify Dependencies
# Format Gantt Chart
\@ Complete Gantt Chart
\@ Submit Gantt Chart
Analysis:
Analysis report
# Document List of Data Requirements
## Document Requirements
## Document Constraints
## Formulate Scope
# Analyse Requirements
# Prepare Report
\@ Complete Analysis Report
\@ Submit Analysis Report
Data Acquisiton
# Prepare Primary Research Techniques
# Conduct Primary Research
# Document Primary Research
# Collect Secondary Research
# Organise/Categorise Data
# Reference Data
\@ Complete Data Acquisition
\@ Submit Data Acquisition
Design
Design Folio
# Prepare Evaluation Criteria
# Develop Three Design Ideas
# Evaluate Design Ideas
# Further Develop Chosen Idea
# Analyse Design Ideas
# Finalise/proofread ideas
\@ Complete Design Folio
\@ Submit Design Folio
Development
Database/Spreadsheet
# Develop Database or Spreadsheet
# Manipulate Data
# Validate Input Data
# Test Output Information
\@ Complete Database/Spreadsheet
\@ Submit Database/Spreadsheet
Infographic/Dynamic Data Visualisation
# Develop Infographic/Dynamic Data Visualisation
# Validate Input Data
# Test Output Information
\@ Complete Infographic/Dynamic Data Visualisation
\@ Submit Infographic/Dynamic Data Visualisation
File Management
# Prepare File Management Plan
# Prepare Securtiy Plan
# Document File Management and Security Report
\@ Complete File Management
\@ Submit File Management
Evaluation
Evaluation Strategy and Report
# Prepare Evaluation Strategies
# Complete Solution Evaluaiton
# Documentation Evaluation Findings
\@ Complete Evaluation Strategy and Report
\@ Submit Evaluation Strategy and Report
Assessment Of Proejct Plan
# Adjust Original Gantt Chart
# Provide Annotations for Each Change
# Document Effectiveness of Gantt Chart
\@ Complete Assessment of Project Plan
\@ Submit Assessment of Project Plan

## Log
Thursday 24/5 | submitted gantt chart 23/5
crit 4 changed to 31st of may